## Pre-Migration Steps Sprint-1
JIRA USER STORY | Component | Steps | Developer
DCR-438 | Enable knowledge permission on user | Setup ¦ ADMINISTRATION ¦ Users ¦ Users
Click on the 'Full Name' hyperlink of the relevant User
Click Edit
In the General Information section, locate and tick the Knowledge User checkbox
Click Save
| Configure Knowledge Settings | Setup ¦ PLATFORM TOOLS ¦ Feature Settings ¦ Service ¦ Knowledge ¦ Knowledge Settings
Under General Settings, ensure the following fields are checked:
1. Allow users to create and edit articles from the Articles tab
2. Activate Validation Status field
3. Allow users to add external multimedia content to HTML in the standard editor
Under Lightning Knowledge Settings, ensure the following fields are checked:
1. Enable Lightning Knowledge
2. Enable automatic loading of rich-text editor when editing an article
Under Article Summaries ¦ Show article summaries in article list views, ensure the following fields are checked:
1. Internal App
2. CheckedCustomer
3. CheckedPartner
Under Knowledge One, ensure the following fields are checked:
1. Highlight relevant article text within search results AND
2. Suggest related articles on cases
Under Language Settings, ensure:
1. Default Knowledge Base Language is set to English AND
2. Single Language is selected
Under Case Settings, ensure the following fields are checked:
1. Use the simple editor when closing a case AND
2. Enable Case Data Category Mapping
Under Chatter Questions Settings, ensure
'Display relevant articles as users ask questions in Chatter (also applies to communities with Chatter)' is checked
Under Knowledge Statistics Settings, ensure 'Enable thumbs up or down voting for article' is checked
| Configure Knowledge Object | Setup ¦ Object Manager Tab, if visible. otherwise
Setup ¦ PLATFORM TOOLS ¦ Objects and Fields ¦ Object Manager
Click on the Label hyperlink for Article (API Name - Article__kav)
Configure Page Layouts, Fields, Record Types and update the relevant Lightning Knowledge Page(s) in this section of Confluence
| Add Knowledge Tab to Application(s) | Setup ¦ PLATFORM TOOLS ¦ Apps ¦ App Manager
Click on the Arrow button corresponding to the app you want to configure and select Edit
In the 'Choose the Tabs' section, ensure 'Articles' is moved to the list of Selected Tabs on the right.
NB: This step assumes the Knowledge Standard Object was renamed to Articles.

## Pre-Migration Steps Sprint-2
JIRA USER STORY | Component | Steps | Task Completed(Yes/No) | Task Completed By(Name of Person who did Task) | Developer | Action
DCR-327 | Setting Organization Email Address | Goto Setup->Quick Search ->Orgwide Address->New-> Name=CTP Assist, Email=CTPAssist@sira.nsw.gov.au Verify the Email Address which is sent to "CTPAssist@sira.nsw.gov.au" |  |  | Prasanth
DCR-191 | OWD setting for case | Goto Setup -> Sharing Settings |  |  | Sudha | Parul

## Migration Sprint-1
S.No | JIRA USER STORY | Component | Type | Developer
1 | DCR 326 | CTP_Claimant_Advisory_Services | Email Template Folder | Parul
|  | CTP_Email_Template_for_submitting_feedback_via_email_web | Email Template | Parul
|  | CTP Case Auto-Response Rule | Case Auto-Response Rule | Parul
|  | Claimant Advisory Services | Organization-Wide Email Addresses | Parul
2 | DCR 109 | CTP_Email_Template_for_Feedback_Case_Escalation | Email Template | Parul
3 | DCR 327/DCR-514 | CTP_Feedback_Case_Page_Layout | Lightning Record Page | Parul
|  | Feedback Case Page Layout | Case Page Layout | Parul
| DCR 187 | CTP_Claimant Advisory Services rule | Email-to-Case | Parul
|  | Case.CTP_Set Case Type for Email to Case | Workflow Rule | Parul
|  | Case.CTP_Set_Case_Type | Field Update | Parul
|  | CTP_CAS_Feedback | Queue | Parul
4 | DCR 500 | CTP_Case_Assignment_Rule | Case Assignment Rule | Parul
5 | DCR 328 | Email Message.CTP_Reopen Case on Reply | Workflow Rule | Parul
|  | Set_Status_to_Re_Open | Field Update | Parul
6 | DCR-319 | CTP_FeedbackForm | Lightning Bundle | Parul
|  | CTP_FetchFeedbackFormController | Apex Class | Parul
|  | CTP_FetchFeedbackFormController_Test | Apex Class | Prasanth
|  | CTP_FeedbackTypeSubType__c | Custom Setting | Parul
|  | CTP_ContactUs | Custom Label | Parul
|  | CTP_FeedbackType | Custom Label | Parul
|  | CTP_FeedbackSubType | Custom Label | Parul
|  | CTP_FeedbackDescription | Custom Label | Parul
|  | CTP_ResponseRequired | Custom Label | Parul
|  | CTP_Submit | Custom Label | Parul
|  | Contact_Us | Community Page | Parul
7 | DCR-557 | CTP_SubmitForApproval | Lightning Bundle | Parul
|  | CTP_SubmitForApprovalController | Apex Class | Parul
|  | CTP_SubmitForApprovalController_Test | Apex class | Prasanth
|  | CTP_SubmitForApproval | Custom Label | Parul
|  | CTP_ApprovalProcessName | Custom Label | Parul
|  | Article__kav.CTP_Submitted_For_Approval__c | Custom Field | Parul
|  | Article__kav.CAS_Lightning_Knowledge_Article_Approval | Approval Process | Parul
8 | DCR-325,DCR-326,DCR-430 | CTP Email Template for submitting feedback via email/web | Email | Prasanth
|  | CTP_CAS_Feedback | Queue | Prasanth
|  | CTP_DRS_Feedback | Queue | Prasanth
|  | CTP Case Assignment Rule | Assignment Rule | Prasanth
9 | DCR-324,DCR-140 | CTP_Feedback_Case_Page_Layout | Lightning Record Page | Prasanth
|  | Feedback Case Page Layout | Page Layout | Prasanth
10 | DCR-434 | Dispute Resolution | Ligthning App | Prasanth
11 | DCR-20 | DRS_Queue_for_Screening | Queue | Parul
12 | DCR-153 | CTP_Email_Template_for_Knowledge_Review from folder CTP-Claimant Advisory Services | email template | sudha
13 | DCR-376 | Language__c on contact | custom picklist field | sudha
|  | InterpreterRequired__c on contact | custom picklist field | sudha
|  | CTP_LanugageIfInterpreterRequired on contact | validation rule | sudha
14 | DCR-559 | All Articles on article | List View | sudha
15 | DCR-558 | CTP_Knowledge_User | permission set | sudha
16 | DCR-360 | CTP_Static_successful_application_Screening_DRS_To_Claimant | email template | sudha
|  | CTP_DRS_Successful_Screening_Communication_to_Claimant1 | email template | sudha
17 | DCR-561 | Claims_Advisory_Services | app | sudha
18 | DCR-266 | CTP_FAQ_Article_Mandatory_Fields on article | validation rule | sudha
|  | FAQ | page layout | sudha
|  | FAQ | record type | sudha
|  | CTP_FAQ_Lightning_Knowledge_Article | record page | sudha
19 | DCR-352 | CTP_How_To_Article_Mandatory_Fields on article | validation rule | sudha
|  | How To | page layout | sudha
|  | How To | record type | sudha
|  | CTP_How_To_Lightning_Knowledge_Article | record page | sudha
20 | DCR-561 | Email_Template_for_Knowledge_Article_Rejection | email template | sudha
21 | DCR-577 + DCR-541 + | CAS Lightning Knowledge Article Approval on article | approval process | sudha
|  | CTP_Answer__c on article | custom field | sudha
|  | CTP_Question__c on article | custom field | sudha
|  | CTP_Steps__c | custom field | sudha
|  | HighLightForArticle | compact layout | sudha
| DCR-376 | Public | RecordType | sudha

## Migration Sprint-2
S.No | Sprint | JIRA USER STORY | Task | Component | Type | Developer | Status | Migrated by(Jenkins/Change Set) | Date | Comment
1 | Sprint 2 Squad 2 | DCR-965 Submit for approval behaviour |  | CTP_SubmitForApprovalController | Apex Class | Parul | Done
|  |  |  | CTP_Rejected | Custom Label | Parul | Done
|  |  |  | CTP_Draft | Custom Label | Parul | Done
|  |  |  | CTP_ApprovalProcessName | Custom Label | Parul | Done
2 | Sprint 2 Squad 2 | DCR-805 Validation Rule for Tasks |  | CTP_Assist_Task | Record Type | Parul | Done
|  |  |  | CTP_Assist_Task_Relate_To_Record | Validation Rule | Parul | Done
|  | DCR-168 |  | CTP_Assist _Task | PageLayout | Parul | Done
3 | Sprint 2 Squad 2 |  |  | CTP_Assist_Task | Quick Action | Parul | Done
4 | Sprint 2 Squad 2 | DCR-652 CAS Team member places Claimant on a 26 week service entitlement | DCR-913 | SIRA Monday to Friday Business Hours | Business hours | Parul | Post Deployment Step
|  | DCR-25 Create Articles from case |  | CTP_Cancel | Custom Label | Parul | Done
|  |  |  | CTP_NewArticleHeader | Custom Label | Parul | Done
5 | Sprint 2 Squad 2 |  |  | CTP_CancelCross | Custom Label | Parul | Done
|  |  |  | CTP_RecordType | Custom Label | Parul | Done
|  |  |  | CTP_Cancel | Custom Label | Parul | Done
|  |  |  | CTP_Next | Custom Label | Parul | Done
|  |  |  | CTP_MasterRecordType | Custom Label | Parul | Done
|  |  |  | CTP_CreateArticleOnCaseController | Apex Class | Parul | Done
|  |  |  | CTP_CreateArticle | Lightning Bundle | Parul | Done
|  |  |  | CTP feedbackCasePageLayout | Pagelayout | Parul | Done
|  |  |  | CTP_CreateArticleOnCaseController_Test | Test Class | Parul | Done
|  | DCR-318 CAS Feedback Case is Escalated |  | CTP Feedback PS | Entitlement Process | Parul | Done
|  |  |  | CTP Feedback v1 | Entitlement Process | Parul | Done
|  |  |  | Case Assignment | Milestone | Parul | Done
|  |  |  | CTP_SetPriorityToStandard | Field Update | Parul | Done
6 | Sprint 2 Squad 2 |  |  | CTP_SetCaseEscalated | Field Update | Parul | Done
|  |  |  | CTP_SetCasePriorityToHigh | Field Update | Parul | Done
|  |  |  | CTP_CaseTrigger | Apex Trigger | Parul | Done
|  |  |  | CTP_CaseTriggerHandler | Apex Class | Parul | Done
|  |  |  | CTP_CaseRecordTypeEntitlementMapping__c | Custom Setting | Parul | Done
|  |  |  | Create Entitlement to Accounts |  | Parul | Post Deployment Step
7 | Sprint 2 Squad 2 | DCR-652 CAS Team member places Claimant on a 26 week service entitlement |  | CTP 26 Week Entitlement PS2 | Entitlement Process | Parul | Done
|  |  |  | CTP 26 Week Entitlement v1 | Entitlement Process | Parul | Done
8 | Sprint 2 Squad 2 | DCR-653 26 week Entitlement: Milestone 1 |  | CTP Milestone 1 26-Week Entitlement | Milestone | Parul | Done
9 | Sprint 2 Squad 2 | DCR-657 26 week Entitlement: Milestone 2 |  | CTP Milestone 2 26-Week Entitlement | Milestone | Parul | Done
10 | Sprint 2 Squad 2 | DCR-658 26 week Entitlement: Milestone 3 |  | CTP Milestone 3 26-Week Entitlement | Milestone | Parul | Done
|  |  |  | CTP Update Next Action StatusNA | Field Update | Parul | Done
|  |  |  | CTP Update Case Status 10W | Field Update | Parul | Done
|  |  |  | CTP_SetCaseSeverityToGreen | Field Update | Parul | Done
|  |  |  | CTP_SetSLAViolationToNo | Field Update | Parul | Done
|  |  |  | CTP_SetActionOnCase | Field Update | Parul | Done
|  |  |  | CTP_New_Task_has_been_assigned_to_you | Workflow Task | Parul | Done
|  |  |  | CTP_SetCaseSeverityToYellow | Field Update | Parul | Done
|  |  |  | CTP_SetSLAViolationToYes | Field Update | Parul | Done
|  |  |  | CTP_SetCaseSeverityToRed | Field Update | Parul | Done
|  |  |  | CTP_SetNumOfViolations | Field Update | Parul | Done
|  |  |  | CTP Claims Assist 26 Week Entitlement Milestone 1 | Workflow rule | Parul | Done
|  |  |  | CTP Claims Assist 26 Week Entitlement Milestone 1 Test | Workflow rule | Parul | Done
|  |  |  | CTP Claims Assist 26 Week Entitlement Milestone 2 | Workflow rule | Parul | Done
|  |  |  | CTP Claims Assist 26 Week Entitlement Milestone 2 Test | Workflow rule | Parul | Done
|  |  |  | CTP Claims Assist 26 Week Entitlement Milestone 3 | Workflow rule | Parul | Done
|  |  |  | CTP Claims Assist 26 Week Entitlement Milestone 3 Test | Workflow rule | Parul | Done
|  |  |  | CTP Update Due Date Lodgement | Field Update | Parul | Done
|  |  |  | CTP Update Next Action StatusMC | Field Update | Parul | Done
|  |  |  | CTP Update Due Date Accident M2 | Field Update | Parul | Done
|  |  |  | CTP Update Due Date Accident M3 | Field Update | Parul | Done
|  |  |  | Case.CTP_ActionDueDate__c | Custom Field | Parul | Done
|  |  |  | Case.CTP_Date_of_accident__c | Custom Field | Parul | Done
|  |  |  | CTP_Assist_Task_Created_23_week_Call | Workflow task | Parul | Done
|  |  |  | CTP_Assist_Task_Created_10_week_Call | Workflow task | Parul | Done
|  |  |  | CTP_Assist_Task_Created_Introduction_Call | Workflow task | Parul | Done
|  |  |  | CTP_New_Task_has_been_assigned_to_you | Workflow task | Parul | Done
|  |  |  | Case.CTP_Next_Action_Status__c | Custom Field | Parul | Done
|  |  |  | Case.CTP_LodgementDate__c | Custom Field | Parul | Done
11 | Sprint 2 Squad 2 | DCR-847 CAS Member takes ownership of a Case |  | CTP_AcceptButton | lightning Bundle | Parul | Done
|  |  |  | CTP_AcceptCaseController | Apex Class | Parul | Done
|  |  |  | CTP_AcceptCaseController_Test | Apex Class | Parul | Done
|  |  |  | CTP_AcceptButton | Custom Label | Parul | Done
|  |  |  | CTP_CASFeedbackQueueName | Custom Label | Parul | Done
|  |  |  | CTP Feedback Case Page Layout | Lightning record page | Parul | Done
12 | Sprint 2 Squad 2 | DCR-965 Submit for approval behaviour |  | CTP_SubmitForApproval | Lightning Bundle | Parul | Done
|  |  |  | CTP_SubmitForApprovalController | Apex Class | Parul | Done
13 | Sprint 2 Squad 2 | DCR-958 CTP Assist - Attach Files to email through libraries |  | CTP_Assist_Member | public Group | Parul | Done
|  |  |  | Library and other steps in post deployment |  | Parul | Post Deployment Step
14 | Sprint 2 Squad 2 | DCR-1215 Automatically create account when creating a contact |  | CTP_ContactBeforeupdate | Apex trigger | Parul | Done
|  |  |  | CTP_ContactTriggerHandler | Apex Class | Parul | Done
15 | Sprint 2 Squad 2 |  | DCR-841 Auto response email - Case Submitted | CTP_Email_Template_for_submitting_feedback_via_email_web | Email Template | Parul | Done
16 | Sprint 2 Squad 2 |  | DCR-858 Auto response email - Case Submitted | CTP_Email_Template_for_Knowledge_Published | Email Template | Parul | Done
21 | Sprint 2 Squad 2 | DCR-640 | DCR-924 | Claims | Support Process | Prasanth | Predeployment step |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-909 | CTP_AssistClaimantSupport | Record Type on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-910 | CTP Claims Case Page Layout | Page Layout on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-910 | CTP Claims Case Page Layout | Lightning Record Page on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-911 | CTP_donotcontacted | Validation Rule on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | status | Field on Case | Prasanth | pending |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | Origin | Field on Case | Prasanth | pending |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | Priority | Field on Case | Prasanth | pending |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_InjuredPersonAccount__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_InjuredPersonContact__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_RepresentativeAccount__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_RepresentativeContact__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_RepresentativeRelationship__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_OtherRelationshipDescription__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_Date_of_accident__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_LodgementDate__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_DoNotContact__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_DoNotContactReason__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_ActionAndOutcome__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_ActionDueDate__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_SeverityColor__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_Severity__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_SLAViolation__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_NumberOfViolations__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | EntitlementId | Field on Case | Prasanth | pending |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_MandatoryForRepresentativeOther | Validation Rule on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_Light_Red | Static Resource | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_Light_Green | Static Resource | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | CTP_Light_Yellow | Static Resource | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | claims advisor | Profile | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  | DCR-912 | system administrator | Profile | Prasanth | Done |  |  | DEV-04
22 | Sprint 2 Squad 2 | DCR-180 |  | CTP_Date_of_birth__c | Field on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_PrimaryPhone__c | Field on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_SecondaryPhone__c | Field on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_ContactMethod__c | Field on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_ContactTime__c | Field on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_RepresentativeRelationship__c | Field on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_RelationshipDescription__c | Field on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_Relationship__c | Field on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_Accessibility__c | Field on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_Homeless__c | Field on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_SelectPastDate | Validation Rule on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_MandatoryForRepresentativeOther | Validation Rule on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_LanugageIfInterpreterRequired | Validation Rule on Contact | Prasanth | Done |  |  | DEV-04
23 | Sprint 2 Squad 2 | DCR-600 |  | CTP_RepresentativeContact__c | Field on Case | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 |  |  | CTP_RepresentativeRelationship__c | Field on Case | Prasanth | Done |  |  | DEV-04
24 | Sprint 2 Squad 2 | DCR-180,DCR-376 |  | CTP_Public | Record Type on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 | DCR-180,DCR-376 |  | CTP Public Page Layout | Pagelayout on Contact | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 | DCR-180 |  | Contact Record Page | Lightning Record Page on Contact | Prasanth | Done |  |  | DEV-04
25 | Sprint 2 Squad 2 | DCR-1255 |  | CTP Case Auto-Response Rule | Case Auto Response Rule | Prasanth | Done |  |  | DEV-04
| Sprint 2 Squad 2 | DCR-1255 |  | CTP Assist Rule | Email-To-Case | Prasanth | Predeployment step |  |  | DEV-04
26 | Sprint 2 Squad 2 | DCR-754 |  | CTP_Entitlement_Case_Mapping | validation rule | Sudha | Done
27 | Sprint 2 Squad 2 | DCR-631 |  | CTP_Discussion_Topic__c on article | custom field | Sudha | Done
|  |  |  | CTP_Talking_Points__c | custom field | Sudha | Done
|  |  |  | CTP Discussion Guide | page layout | Sudha | Done
|  |  |  | Discussion Guide Lightning Knowledge Article | record page | Sudha | Done
|  |  |  | CTP_Discussion_Guide_Mandatory_Fields | validation rule | Sudha | Done
|  |  |  | Discussion Guide | record type | Sudha | Done
28 | Sprint 2 Squad 2 | DCR-838 |  | CTP FAQ | page layout | Sudha | Done
|  |  |  | CTP How To | page layout | Sudha | Done
|  |  |  | FAQ Lightning Knowledge Article | record page | Sudha | Done
|  |  |  | How To Lightning Knowledge Article | record page | Sudha | Done
|  |  |  | FAQ | Record Type | Sudha | Done
|  |  |  | How To | Record type | Sudha | Done
29 | Sprint 2 Squad 2 | DCR-191 |  | OWD setting for case | OWD | Sudha | Predeployment step
|  |  |  | CAS Read/Write Case Level Access | case sharing rule | Sudha | Done
|  |  |  | CAS_ReadOnly_Case_Level_Access | case sharing rule | Sudha | Done
30 | Sprint 2 Squad 2 | DCR-561 |  | CTP assist | app | Sudha | Done
31 | Sprint 2 Squad 2 | DCR-634 |  | CTP Email Template Administration | permission set | Sudha | Done
32 | Sprint 2 Squad 2 | DCR-172 |  | CTP Set Reminders | page layout | Sudha | Done
33 | Sprint 2 Squad 2 | DCR-906 |  | feedback | record type | Sudha | Done
34 | Sprint 2 Squad 2 | DCR-760 |  | Email Template for Knowledge Article Rejection | email template | Sudha | Done
|  |  |  | mail Knowledge Article Rejection | Email Alert Name | Sudha | Done
35 | Sprint 2 Squad 2 | DCR-139 |  | Feedback Type | field on case | Sudha | Done
|  |  |  | Feedback sub-type | field on case | Sudha | Done
36 | Sprint 2 Squad 2 | DCR-600 + 180 |  | CTP_Representative_None | validation rule on case | Sudha | Done
37 | Sprint 2 Squad 2 |  |  | CTP_AdditionalInformation__c | field on contact | Sudha | Done
38 | Sprint 2 Squad 2 |  |  | CTP_DateOfBirth__c | Field on Contact | Sudha | Done
39 | Sprint 2 Squad 2 |  |  | CTP_Minor__c | Field on Contact | Sudha | Done
40 | Sprint 2 Squad 2 |  |  | CTP_Opt_Out_of_Case_Email_Updates__c | Field on Contact | Sudha | Done
|  |  |  | All_Articles | Article List View | Sudha | Done
|  |  |  | archived_articles | Article List View | Sudha | Done
|  |  |  | draft_articles | Article List View | Sudha | Done
|  |  |  | published_articles | Article List View | Sudha | Done
|  |  |  | Knowledge_Manager | Queue | Sudha | Done
|  |  |  | Legal_Team_Knowledge_Article_Reviewers | Queue | Sudha | Done
|  |  |  | CTP Assist - Claimant Support Cases | Case List View | Prasanth | Done

## Post-Migration Steps Sprint-1
JIRA USER STORY | Component | Steps | Developer
DCR-514 | Page layout Assignment | Click on User name on the right side top of the page -> Click on Switch to Lightning Experince ->Goto Setup -> Object Manager--> Case--->Lightning record page---> CTP feedback--->edit--->Activation --> Click on App,Record Type and Profile --->Add Assignment -->Add as mentioned in below Application -> CTP Assist, Service Console, Dispute Resolution Record Type -> Feedback Profile -> CTP Assist, System Administrator | Parul
DCR-308 | Enable Web-to-Case | Go To Set Up --> Search in Quick Find--->Web-to-Case--->Check enable web-to-case--->Set Default Case Origin as Web | Parul
DCR-1339 | Generating the Web-to-Case HTML Generator | Go To Setup --> Search in Quick Find --> Web-to-case HTML Generator -> Add Contact Name, Email, Phone, Subject, Description -> Click on Generate for editing the Webform to create the case. Here is the Webforms for Web-to-Case and Thank you for the Dev05 Environment
DCR-319 | Adding Records in Custom Setting | Go to Set Up --> Search in Quick Find --->Custom Setting--->CTP_FeedbackTypeSubType__c--->Manage--->add the following data to custom Setting | Parul
Name Case Type Feedback SubType Feedback Type 1 CTP Assist Motor Accident Injury Claims Enquiry 2 CTP Assist CTP Green Slips Enquiry 3 DRS Claims Disputes Enquiry 4 CTP Assist Our Contact Support Services Feedback 5 DRS Our Dispute Resolution Services Feedback 6 CTP Assist The CTP Scheme Feedback 7 CTP Assist CTP Green Slips Feedback 8 CTP Assist About an Insurer Feedback 9 CTP Assist Our Contact Support Services Compliment 10 DRS Our Dispute Resolution Services Compliment 11 CTP Assist The CTP Scheme Compliment 12 CTP Assist About an Insurer Compliment 13 CTP Assist Our Contact Support Services Complaint 14 DRS Our Dispute Resolution Services Complaint 15 CTP Assist The CTP Scheme Complaint 16 CTP Assist CTP Green Slips Complaint 17 CTP Assist About an Insurer Complaint
DCR-187/DCR-430 | Adding Members to Queue | Go To Set Up--> Search in Quick Find --->Queue--->edit and Add members as mentioned below | Parul
CTP_CAS_Feedback - Role:CAS Manager ,Customer Portal User , Role :CAS Agent
CTP_DRS_Feedback - Customer Portal User
DCR-20 | Add Members to Queue | Go To Set Up--> Search in Quick Find --->Queue--->edit and Add members as mentioned below DRS_Queue_for_Screening - Role and Internal Subordinates : DRS | Parul
DCR-319 | Add Contact_Us page as tab on Public community | Goto Setup -> Search in Quick Find ->All Communities ->Search For Public Community -> Click on Builder -> Add Contact Us Page on the Menu
DCR-577 | Chatter Settings | chatter settings(In addition, to allow Approval requests to be sent as Chatter Notifications, go to Setup ¦ PLATFORM TOOLS ¦ Feature Settings ¦ Chatter ¦ Chatter Settings. Ensure both of the following checkboxes are ticked: >Chatter Settings ¦ Turn on Chatter and Global Search features....Enable >Approval Posts ¦ Allow users to receive approval requests as posts ¦ Allow Approvals) | sudha
DCR-559 | Organize all list views on Article object in the same order | Go to Setup-> Object Manager -> Article -> Click on any of the list views -> Verify the below oder is the same Article Number,Article Title,Article Record Type,Summary,Validation Status,Publication Status,Published Date | sudha
Verify all the Profile Settings in the Target Org

## Post-Migration Steps Sprint-2
S.No | Sprint | JIRA USER STORY | Component | Steps | Developer
1 | Sprint-2 Squad 2 | DCR-805 | Provide 'CTP Assist Task' record type on Task access to Claims Advisor profile | 1. Goto Set Up--->Quick Find--->Profile--->CTP Assist--->task--->Search for Record Type Settings of Task -->Click on Edit -> Select " CTP Assist Task" in the Available Record types ->Add to selected Record types -> Save | Parul
Parul
2 | Sprint-2 Squad 2 | DCR-168 | Give 'CTP_Assist _Task' Page Layout access to record type and profile | 1. Go To Set up-->Object manager-->Task--->Page layout--->Pagelayout assignment-->edit--> For 'CTP Assist' record type and 'Claims advisor' profile add CTP_assist_Task Pagelayout -> Save | Parul
|  |  | Add 'CTP_Assist_Task' Quick Action on Pagelayout | 1. Goto Set up-->Object Manager--->Case --->CTP Feedback Case pagelayout --->Edit--->Add 'CTP_Assist' Quick action on page layout -> Save 2. Set up-->Object Manager--->Case--->CTP Claims Case Page Layout --->Edit--->Add 'CTP_Assist' Quick action on pagelayout -> Save | Parul
Parul
3 | Sprint-2 Squad 2 | DCR-913 | Setting up the SIRA Monday to Friday Business Hours | Goto Setup -> Business Hours -> Add New -> Business Hours Name= "SIRA Monday to Friday Business Hours", Business Hours = Monday to Friday will be the working hours from 9 AM to 5 PM and Sunday, Saturday= no hours, Active= enable -> Save | Parul
4 | Sprint-2 Squad 2 | DCR-318 | Create Entitlement for SIRA Account | 1. Create a account with Record Type= " Internal ", Account name ="State Insurance Regulator Authority" Website = "http://www.sira.gov.nsw.au" 2. Go to Entitlement related List--->Add New entitlement ---> In Entitlement Process fields select--->CTP Feedback PS process and save 3. Repeat point-2 to add "CTP Damages Entitlement" and " CTP Non Damages Entitlement" | Parul
6 | Sprint-2 Squad 2 | DCR-652 | Add Records to custom setting | Setup -> Custom Setting -> CTP_CaseTypeMapping__c -> Manage -> Add following data | Parul
|  |  |  | Name Case Type Origin Priority Status RecordType Location 1 CAS Web Low New Feedback Organization 2 DRS Web Low New Feedback Organization | Parul
7 | Sprint-2 Squad 2 | DCR-963,958 | Create Library 'CTP Assist Library ' and Add member to library admin role | First Enable " Salesforce CRM Content User" in User Details:- My profile-> userdetails->edit-> Enable salesforce CRM Content User -> Save 1. Goto-->Salesforce Classic--->Tabs--->File-->Click on Asset Library ->Click on Go to Library Details--->Under My Libraries--->New---> Create CTP Assist library-->Description add 'Library for CTP Assist Member public group' 2. Select CTP Assist Library--->under members section---> Add Member-->Select Public Group--> Select CTP Assit Member and add -> Click on Next -->Assign Library administrator role ->Save | Parul
8 |  | DCR-924 | Adding Values to Claims-Support Process | Goto Setup -> Support Process -> Open Claims -> Add Values in the Selected Values 1.New, Introduction Call 2.10 week Call 3. 23 week call 4. 75 week review 5. 20 month call 6. 2 year review 7. 3 month damages review 8. 3 year damages review 9. 5 year damages review 10. Closed(Closed). | Prasanth
|  |  | Compact layout Assignement on Contact | Goto Setup -> Object Manager -> Contact ->Compact layout-> compact layout assignment -> Edit-> Assign to CTP_Public Record type as System Default layout
|  |  | Edit the CTP Claims Case Pagelayout in Lightning Record Page | Goto Setup -> Object Manager ->Case -> Lightning Record Pages -> CTP Claims Case Page layout-> Click on Assignments -> Add App Default as CTP Assist and Record type=:CTP Assist Claimant Support, Profile=CTP Assist and System Administrator
|  |  | Add "Take Ownership" button to CTP Feedback case pagelayout lightning reocrd page | Goto Setup -> Object Manager -> Case -> Lightning Record Page -> CTP Feedback Case page layout -> Edit -> Select CTP_AcceptButton in Custom components -> Add in the top of the feed
|  |  | Adding Permission Sets to CTP Assit team | Goto Setup -> Users-> Search for CTP Assist Team Users-> knowledge User permission set

## Pre Migration Steps Sprint-3
JIRA USER STORY | Component | Steps | Developer | TO Do
DCR-1312 | Add "Cancelled' value in Status field on Task | Goto Setup->Object manager -> Task-> Fields -> Status -> Add "Cancelled" value and make it as Closed, and apply only for CTP Assist Task Record Type only | Prasanth
| Ensure all picklist values for standard picklist fields in target environment | If there is no values found add the values in target environment
| Create users(Users for sandbox testingand not for production) | castestuser1@capgemini.com.ctpdev02, coy3uaccastestuser1@capgemini.com.ctpdev02, castestuser1@capgemini.com | sudha kumari
| Create users(Users for sandbox testingand not for production) | roger.gomez.claims@gmail.com | sudha kumari
DCR-684 | Add Records to custom setting | Goto set up-->Custom Settings--->CTP_CaseRecordTypeEntitlementMapping--->Manage--->Add the following data (Entitlement process name is the record id Of entitlement associated with the account-- Account and its related list entitle process is created as a post deployement step sprint-2 in 17th point for verifying and adding the record id in the record) | Parul

## Post MIgration Steps Sprint-3
JIRA USER STORY | Component | Steps | Developer
| Enable Live Agent | Goto Setup-> Live Agent -> Enable
| Enable Omni Channel | Goto Setup->omni channel settings -> click on enable
| Compact layout Assignment in Contact | Goto Setup-> Oject manager-> Contact -> Compact layout -> Edit Assignment -> Assign System default to all other Record types except OLCN Record Type
| CTP Feedback Lightning record page Assignment | Goto Setup->Object manager -> Case-> Lightning record page -> CTP Feedback -> Edit -> Assign Assignments -> 1. App -> CTP Assist 2. Record Type -> Feedback 3. Profile -> CTP Assist, System Admin
| Assign "Take ownership Case" button to lightning record page | Goto Setup-> Object Manager -> Case -> Lightning Record Page ->OLCN Case Record page ->Add CTP_Accept Custom Button in the top of the page -> Save
| CTP Claimant Support Record page Assignmnet | Goto Setup->Object Manager -> Case -> Lightning Record Page ->CTP Claimant Support Record page ->Edit -> Click on Assignments -> Add Compensate to Relative Recod type , CTP Assist Application, CTP Assit,System Admin Profiles
| Modify Data Category Assignments | Goto Setup-> Data Category Assignments -> CTP Assist -> Edit Category Group Visibility -> Add 1. All-CTP Green Slips 2. All-Claims
| Add Data Category Mapping | Goto Setup -> Data Category Mappings -> Case field=Feedback sub type, Data category group= CTP Assist and click on Add
DCR-684 | Associate Entitlement Process to Account Entitlement Record | 1. Goto Setup -> Go To Account Tab--->State Insurance Regulator Authority--->Related List--->Entitlements--->Associte the entitlements created in pre deployment steps to mentioned below processes
CTP Damages Entitlement --->Entitlement Process (CTP Damages Entitlement)
CTP Feedback PS ------>Entitlement Process(CTP Feedback PS)
CTP Non-Damages Entitlement----->Entitlement Process(CTP Non-Damages Entitlement)
DCR-1359 | Verify 'Claims Damages" Support Process | Go To Set Up--->Support Process---> Claims Damages--->Verify if following values are selected 1. 3 month review 2. 3 year review 3. 5 year review 4. Closed(closed)
DCR-1359 | Verify "Claims" Support Process | Go To Set Up--->Support Process---> Claims --->Verify if following values are selected New Introduction Call 10 week call 23 week call 75 week review 20 month call 2 year review closed(closed)
DCR-1359 | Assign Support Process to Record Types | Goto Setup ->Go To Object Manager---->Case--->Record Type---> CTP Assist - Non-damages--->Edit--->Verify if support Process Claims is selected
Go To Object Manager---->Case--->Record Type---> CTP Assist - Damages--->Edit--->Verify if support Process Claims Damages is selected
DCR-1359 | Set FLS for Custom Fields - Case.CTP_Late_Claim_Flag__c,CTP_Date_of_Common_Law_Notification__c | Go To Case--->Fields--->CTP_Late_Claim_Flag__c,CTP_Date_of_Common_Law_Notification__c---> Set field Level Security to visible for CTP Assist Profile and System Admin
DCR-1292 | Set CTP Assist Profile User as Live Agent User | Goto Setup -> Profile--->CTP Assist--->Sarah Barnes--->Edit User --->Select Live Agent user -> Save
UCD- Integration-Mule Stub EndPoint | Remote Site Setting | Remote Site Name: UCDMulesoft Remote Site URL: http://dfsi-ucd-claimant.au.cloudhub.io Description: This is the mule stub URL created for UCD Integration.
Creating New CTP Assist App | Goto Setup -> App Manager -> Click on New -> Provide Name -> "CTP Assist" Developer Name -> CTP_Assist_App Description -> Manage Compulsory Third Party cases, including Claims Assistance, Notifications and Feedback. Add Image -> Navigation Style(App Options) -> Console navigation Utility Bar -> Notes, History, Chatter Feed, Phone,omni Channel Select Items -> Home, Cases, Contacts, Articles, Reports, Dashboards, Chatter, Accounts, Approval Requests, Calendar, Files, Social Posts, Tasks, Live Chat Transcripts, Omni Supervisor(Beta). Profiles -> CTP Assist, System Adminstrator

## Sprint 3
S.No | Sprint | JIRA USER STORY | Task | Component | Type | Developer | Status | From Environment | To Environment | Migrated by(Jenkins/Change Set) | Date | Comment
|  |  |  | OLCN_CaseTriggerHelper | Class | Sridevi |  | Dev02
|  |  |  | OLCN_MetaUtility | Class | Sridevi |  | Dev02
|  | DCR-1395 |  | CTP_Status Changed other than Closed | Workflow Rule | Prasanth | Done
|  | DCR-1395 |  | CTP_Changing_Case_Close_Reason_to_None | Field Update | Prasanth | Done
|  | DCR-1395 |  | CTP_Reopen Case on Reply | Workflow Rule | Parul | Done
|  | DCR-1395 |  | Set_Status_to_Re_Open | Field Update | Parul | Done
|  | DCR-1395 |  | CTP_FU_New_Email_Received | Field Update | Parul | Done
|  | DCR-1395 |  | CTP_SetCaseCloseCommentsToNone | Field Update | Parul | Done
|  | DCR-1395 |  | SetCaseClosedReasonToNone | Field Update | Parul | Done
|  | DCR-1395 |  | Case Closed Reason | Field on Case | Prasanth | Done
|  | DCR-1395 |  | Case Closed Comment | Field on Case | Prasanth | Done
|  | DCR-1312 |  | CTP Assist - Claimant Support Auto Close | Process Builder | Prasanth | Done
|  | DCR-1312 |  | CTP Assist Task | Record Type on Task | Prasanth | Done
|  | DCR-1312 |  | Status | Field on Task | Prasanth | Standard Field
|  | DCR-855 |  | FAQ | Record Type on Article | Prasanth | Done
|  | DCR-855 |  | Discussion Guide | Record Type on Article | Prasanth | Done
|  | DCR-855 |  | How To | Record Type on Article | Prasanth | Done
|  | DCR-994 |  | 1.Close_Case 2. Predefined Values -> Case_Closed_Reason__c,Close_Case_QuickAction__c | Action on Case | Prasanth | Done
|  | DCR-409 |  | CTP Assist - Claim Notification | ListView on Case | Prasanth | Done
|  | DCR-409 |  | CTP Assist - Open Claim Notification | ListView on Case | Prasanth | Done
|  | DCR-409 |  | CTP Assist - Feedback | ListView on Case | Prasanth | Done
|  | DCR-409 |  | CTP Assist & DRS - Feedback | ListView on Case | Prasanth | Done
|  | DCR-409 |  | CTP Assist - Claimant Support Cases | ListView on Case | Prasanth | Done
|  | DCR-409 |  | CTP Assist - My Claimant Support Cases | ListView on Case | Prasanth | Done
|  | DCR-409 |  | CTP Assist - Complex Support Queue | ListView on Case | Prasanth | Done
|  | DCR-409 |  | CTP Assist - General Support Queue | ListView on Case | Prasanth | Done
|  | DCR-409 |  | CTP Assist Manager | Role | Prasanth | Done
|  | DCR-1394 |  | Insurer Process status | Field on Case | Prasanth | Done
|  | DCR-1394 |  | Insurer Process status | Field on Case | Prasanth | Dev02
|  | DCR-1394 |  | Insurer Process status to WarmTransfer | Workflow Rule | Prasanth | Dev02
|  | DCR-1394 |  | Insurer_Process_Status_to_Warm_transfer | Field Update | Prasanth | Dev02
|  | DCR-409 |  | Claims Notification | Record Type on Case | Prasanth | Done
|  |  | DCR-1383 | CTP Date Finalised on date | custom field | sudha | Done
|  |  | DCR-1256 | CTP_DueDateFuture on task | validation rule | sudha | Done
|  |  |  | CTP_DOBFutureDate on contact | validation rule | sudha | Done
|  |  |  | CTP_AccidentDateInPastForClaimsCase on case | validation rule | sudha | Done
|  |  |  | CTP_LodgementDatePastDate on case | validation rule | sudha | Done
|  |  |  | CTP_LodgementDateGreaterThanAccidentDate on case | validation rule | sudha | Done
|  |  | DCR-1396 | CTP Assist Standard Support Cases | public group | sudha | Done
|  |  | DCR-1397 | Standard Support Cases on case | list view | sudha
Compensation to Relatives record type on case sudha
|  |  |  | Date Finalised on case | date | sudha
|  |  |  | Risk Outcome on case | picklist | sudha | Done
|  |  | DCR-686 | CTP Compensation to Relatives Page Layout | page layout | sudha | Done
|  |  | DCR-686 | CTP Compensation to Relatives Page Layout | Record page | sudha
|  |  | DCR-1477 | OLCN_CaseTriggerHelper | Class | Sridevi |  | Dev02
|  |  | DCR-1477 | OLCN_MetaUtility | Class | Sridevi |  | Dev02
|  |  | DCR-1477 | OLCN_CaseTriggerHandler | Class | Sridevi |  | Dev02
|  |  | DCR-1383 | CTP Date Finalised on case | custom field | sudha
|  |  | DCR-1256 | CTP_DueDateFuture on task | validation rule | sudha
|  |  |  | CTP_DOBFutureDate on contact | validation rule | sudha
|  |  |  | CTP_AccidentDateInPastForClaimsCase on case | validation rule | sudha
|  |  |  | CTP_LodgementDatePastDate on case | validation rule | sudha
|  |  |  | CTP_LodgementDateGreaterThanAccidentDate on case | validation rule | sudha
|  |  | DCR-1396 | CTP Assist Standard Support Cases | public group | sudha
|  |  | DCR-1397 | Standard Support Cases on case | list view | sudha
|  |  | DCR-191 | CAS_Read_Write_Case_Level_Access | sharing rule | sudha
|  |  |  | CAS_ReadOnly_Case_Level_Access | sharing rule | sudha
|  |  | DCR-635 | Knowledge Manager | permission set | sudha
|  |  | DCR-686 | Compensation to Relatives | support process | sudha
Compensation to Relatives record type on case sudha
|  |  |  | compensation to relatives | entitlement | sudha
|  |  |  | compensation to relatives | milestone | sudha
|  |  | DCR-806 | Date of Accident on case | date | sudha
|  |  |  | Lodgement Date on case | date | sudha
|  |  |  | CTP Date of Common Law Notification on case | date | sudha
|  |  |  | Date Finalised on case | date | sudha
|  |  |  | End date of service/benefit period on case | date | sudha
|  |  |  | Accident Number on case | text | sudha
|  |  |  | Fault Status on case | picklist | sudha
|  |  |  | Risk Outcome on case | picklist | sudha
|  |  |  | Fatality on case | Checkbox | sudha
|  |  |  | Managing Insurer Code on case | picklist | sudha
|  |  |  | Managing Insurer Claim Number on case | text | sudha
|  |  |  | Minor Injury Decision on case | picklist | sudha
|  |  |  | Outcome of WPI Assessment/Indication on case | picklist | sudha
|  |  |  | Estimate of Injury Severity (EIS) on case | picklist | sudha
|  |  |  | Statutory benefit liability Status on case | text | sudha
|  |  |  | Common Law Liability Status on case | picklist | sudha
|  |  |  | Claimant Capacity Status on case | picklist | sudha
|  |  |  | Return to Work Status Code on case | picklist | sudha
|  |  | DCR-1403 | CTP Case Assignment Rule | assignment rule | sudha
|  |  | DCR-806 | CTP Claimant Support Page Layout | page layout | sudha
|  |  | DCR-686 | CTP Compensation to Relatives Page Layout | page layout | sudha
|  |  | DCR-806 | Contributory Negligence Assessment (%) on case | number field | sudha
|  |  | DCR-686 | CTP Compensation to Relatives Page Layout | Record page | sudha
|  |  | DCR-806 | Stat Benefit Reason for Decline | picklist field | sudha
|  |  | DCR-806 | Stat Benefit Claim Status | picklist field | sudha
|  |  |  | Stat Benefit Liability Decided Date | picklist field | sudha
|  |  |  | Stat Benefit Reason for Decline | picklist field | sudha
|  |  |  | Stat Benefit Liability Status | picklist field | sudha
|  |  | 1.DCR-1292 2. DCR-1015 3. DCR-880 4. DCR-879 5. DCR-878 6. DCR-876 7. DCR-875 8. DCR-685 9. DCr-684 | CTP Non-Damages Entitlement | Entitlement Process | Parul
|  |  |  | CTP Non-Damages Entitlement v1 | Entitlement Process | Parul
|  |  |  | CTP Milestone 1 Non-Damages Entitlement | Milestone | Parul
|  |  |  | CTP Milestone 2 Non-Damages Entitlement | Milestone | Parul
|  |  |  | CTP Milestone 3 Non-Damages Entitlement | Milestone | Parul
|  |  |  | CTP Milestone 4 Non-Damages Entitlement | Milestone | Parul
|  |  |  | CTP Milestone 5 Non-Damages Entitlement | Milestone | Parul
|  |  |  | CTP Update Next Action StatusNA | Field Update | Parul
|  |  |  | CTP Update Case Status 10W | Field Update | Parul
|  |  |  | CTP_SetCaseSeverityToGreen | Field Update | Parul
|  |  |  | CTP_SetSLAViolationToNo | Field Update | Parul
|  |  |  | CTP_SetActionOnCase | Field Update | Parul
|  |  |  | CTP_SetCaseSeverityToYellow | Field Update | Parul
|  |  |  | CTP_SetSLAViolationToYes | Field Update | Parul
|  |  |  | CTP_SetCaseSeverityToRed | Field Update | Parul
|  |  |  | CTP_SetNumOfViolations | Field Update | Parul
|  |  |  | CTP Update Case Status 23W | Field Update | Parul
|  |  |  | CTP Update Case Status 75W | Field Update | Parul
|  |  |  | CTP_SetDueDateToNull | Field Update | Parul
|  |  |  | CTP Set Case Status to 20 month call | Field Update | Parul
|  |  |  | CTP Update Case Status to 2 year Review | Field Update | Parul
|  |  |  | CTP Claims Assist Non-Damages Entitlement Milestone 1 | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Non-Damages Entitlement Milestone 1 Test | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Damages Entitlement Milestone 2 | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Damages Entitlement Milestone 2 Test | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Non-Damages Entitlement Milestone 3 | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Non-Damages Entitlement Milestone 3 Test | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Non-Damages Entitlement Milestone 4 | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Non-Damages Entitlement Milestone 4 Test | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Non-Damages Entitlement Milestone 5 | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Non-Damages Entitlement Milestone 5 Test | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Non-Damages Entitlement Milestone 6 | Workflow Rule | Parul
|  |  |  | CTP Claims Assist Non-Damages Entitlement Milestone 6 Test | Workflow Rule | Parul
|  |  |  | CTP Update Due Date Lodgement | Field Update | Parul
|  |  |  | CTP Update Next Action StatusMC | Field Update | Parul
|  |  |  | CTP Update Due Date Accident M3 | Field Update | Parul
|  |  |  | CTP Update Due Date Accident M2 | Field Update | Parul
|  |  |  | CTP Set Action Due Date For 75 week | Field Update | Parul
|  |  |  | CTP Set Action Due Date for 20 month cal | Field Update | Parul
|  |  |  | CTP Set Action Due Date for 2 year call | Field Update | Parul
|  |  |  | CTP Assist Task Created: Introduction Call | Workflow Task | Parul
|  |  |  | CTP Assist Task Created: 23 week Call | Workflow Task | Parul
|  |  |  | CTP Assist Task Created: 75 week Call | Workflow Task | Parul
|  |  |  | CTP Assist Task Created: 20 month Call | Workflow Task | Parul
|  |  |  | CTP Assist Task Created:2 year call | Workflow Task | Parul
|  |  |  | CTP Assist Task Created: 10 week Call | Workflow Task | Parul
Parul
|  |  |  | CTP Damages Entitlement | Entitlement Process | Parul
|  |  |  | CTP Milestone 1 Damages Entitlement | Milestone | Parul
|  |  |  | CTP Milestone 2 Damages Entitlement | Milestone | Parul
|  |  |  | CTP Milestone 3 Damages Entitlement | Milestone | Parul
|  |  |  | CTP Update Case Status 3Y | Field Update | Parul
|  |  |  | CTP Case Status To 5Y Review | Field Update | Parul
|  |  |  | CTP Claims Assist Damages Entitlement Milestone 1 | Workflow | Parul
|  |  |  | CTP Claims Assist Damages Entitlement Milestone 1 Test | Workflow | Parul
|  |  |  | CTP Claims Assist Damages Entitlement Milestone 2 | Workflow | Parul
|  |  |  | CTP Claims Assist Damages Entitlement Milestone 2 Test | Workflow | Parul
|  |  |  | CTP Claims Assist Damages Entitlement Milestone 3 | Workflow | Parul
|  |  |  | CTP Claims Assist Damages Entitlement Milestone 3 Test | Workflow | Parul
|  |  |  | CTP Update Due Date Lodgement 13W | Field Update | Parul
|  |  |  | CTP Update Due Date Lodgement 3Y | Field Update | Parul
|  |  |  | CTP Set Action Due Date For 5 year | Field Update | Parul
|  |  |  | CTP Assist Task Created: Damages 3M Call | Workflow Task | Parul
|  |  |  | CTP Assist Task Created: 3 Year Review | Workflow Task | Parul
|  |  |  | CTP Assist Task Created: 5 Year Call | Workflow Task | Parul
Parul
|  |  |  | CTP_CaseTriggerHandler | Apex Class | Parul
|  |  |  | CTP_CaseTrigger | Apex Trigger | Parul
|  |  |  | CTP_CaseRecordTypeEntitlementMapping | Custom Setting | Parul
|  |  |  | CTP_10_week_call_Case_Status | Custom Labels | Parul
|  |  |  | CTP_20_Month_Call_Case_Status | Custom Labels | Parul
|  |  |  | CTP_23_Week_Call_Case_Status | Custom Labels | Parul
|  |  |  | CTP_2_Year_Review_Case_Status | Custom Labels | Parul
|  |  |  | CTP_3_month_review_Case_Status | Custom Labels | Parul
|  |  |  | CTP_3_Year_Review_Case_Status | Custom Labels | Parul
|  |  |  | CTP_5_Year_Review_Case_Status | Custom Labels | Parul
|  |  |  | CTP_75_week_review_Case_Status | Custom Labels | Parul
|  |  |  | CTP_Damage_Milestone_name_1 | Custom Labels | Parul
|  |  |  | CTP_Damage_Milestone_name_2 | Custom Labels | Parul
|  |  |  | CTP_Damage_Milestone_name_3 | Custom Labels | Parul
|  |  |  | CTP_Introduction_Call_Case_Status | Custom Labels | Parul
|  |  |  | CTP_Milestone_Name_1 | Custom Labels | Parul
|  |  |  | CTP_Milestone_Name_2 | Custom Labels | Parul
|  |  |  | CTP_Milestone_name_3 | Custom Labels | Parul
|  |  |  | CTP_Milestone_name_4 | Custom Labels | Parul
|  |  |  | CTP_Milestone_name_5 | Custom Labels | Parul
|  |  |  | CTP_Milestone_name_6 | Custom Labels | Parul
|  |  |  | CTP_Must_Call | Custom Labels | Parul
Parul
|  |  | DCR-1359 | Case.CTP_Assist_Damages | Record Type | Parul
|  |  |  | Case.Claims Damages | Support Process | Parul
|  |  |  | Case.Claims | Support Process | Parul
|  |  |  | Case.CTP_Late_Claim_Flag__c | Custom Field | Parul
|  |  |  | Case.CTP_Date_of_Common_Law_Notification__c | Custom Field | Parul
|  |  |  | CTP_Assist_Non_damages | Record Type -Renmaing | Parul
|  |  |  | CTP Flip Damages case to Non-Damages | Workflow rule | Parul
|  |  |  | CTP Flip NonDamages case to Damages | Workflow rule | Parul
|  |  |  | Flip Record Type to Damages | Field Update | Parul
|  |  |  | Flip Record Type to Non-Damages | Field Update | Parul
|  |  |  | CTP Case Assignment Rule | Assignment Rule | Parul
|  |  | UCD- Integration-Mule Stub EndPoint | CTP_UCDDetailsController | Class | Ankit | Dev02

## Live Agent
CTP_Assist | Live Agent Skills | Skills | Goto Setup -> Skills -> New ->Name = CTP_Assist , Description = Answer questions on general CTP assistance. Add Users -> Add CTP Assist & System Admin Profile -> Save | KD | CTPDEV04
1. Live_Chat | Setting Chat Buttons and Automated Invitations | Chat Buttons and Automated Invitations | Goto Setup -> Chat buttons and Automated Invitations -> New -> Type= Chat button Name= Live Chat language = English Auto Greeting= hey {!LiveAgent_VisitorName}, what can we do for you? Routing Type = OMNI Queue = CTP Assist Feedback Enable Queue = True Overall Queue Size = 10 -> Save | KD | CTPDEV04
Note: Copy the Code generated and paste it on a new notepad++ → call this as 'A'.
CTP_Assist | Live Agent Configurations | Live Agent Configurations | Default Skill Filter: CTP Assist Default Button Filter: Live Chat Assigned Skills: CTP Assist | KD | CTPDEV04
Grant access to all CTP Assist profile users
SIRA_Public_Website | Live Agent Deployments | Deployments | Create a new deployment as mentioned and check with UI/UX team for branding images if required for DEV05. | KD | CTPDEV04
Note: Copy the code generated and paste it on the same notepad below the code 'A' → call this as 'B'.
CTP_Assist | Snap-Ins Deployments | Switch to Lightning → Service Setup → Snap-ins | Create a new Snap-ins deployment called CTP Assist as per following steps: | KD | CTPDEV04
1. Site Endpoint to Public_Community
2. Live Agent Deployment to
a. SIRA Public Website (row#65 code B)
b. Live Agent Button to Live_Chat (row# 63)
3. Branding as is in DEV04
4. Enable the Pre-Chat page with:
a. Object: Contact, Case
b. Pre-Chat fields: Name, Email, Subject
c. Status: Enabled
d. and make sure you activate this.
5. Click on 'Get Code' to get the code from Snap-In code snippets → call this as code 'C' and paste it above the code 'A' (at the TOP) on the same notepad and save this file as CTP Assist - Live Chat.html and distribute this html to relevant users/admins for DEV05.
Enable Omni Channel | Omni Channel settings | Omni Channel | Enable Omni-Channel under Omni-Channel Settings (in Classic) | KD | CTPDEV04
CTP_Assist_Feedback_Cases | Service Channels | Omni Service Channel on Case object | As is in DEV04 to DEV05. | KD | CTPDEV04
Note: Once you enable the Omni Channel, Salesforce would auto create an 'Live Agent' service channel for Live Chat Transcript object.
CTP_Assist_Feedback_Cases | Routing Configurations | Omni Channel Routing config | Follow and map the settings as is in DEV04. | KD | CTPDEV04
AND
Enable this routing config for 'CTP Assist Feedback' cases queue.
CTP_Assist_Feedback | Case Queue | Queue | Updated with supported objects as Case, Live Chat Transcript, Live Agent Session | KD | CTPDEV04
AND
Grant access (as members) to all required business/system admin users as mentioned
AND
Routing Confgiuration linked to: CTP Assist Feedback Cases
Available | Service Presence Statuses | Service Presence Statuses | Create and enable them for following service channels: | KD | CTPDEV04
Busy |  |  | CTP Assist Feedback Cases
Offline |  |  | Live Agent
CTP_Assist | Presence Configurations | Presence Configurations | Setup as is in DEV04 | KD | CTPDEV04
AND
Assign/Grant access to all users as required.
CTP_Live_Agent_Supervisor | Permission Set | Pemission Set for Omni supervisors | Deploy this permission set from DEV04 to DEV05 | KD | CTPDEV04
CTP_Assist_App (under App Manager in Lightning) | Lightning App | Lightning App | Edit and Follow all the App settings and create the same in DEV05 as is. | KD | CTPDEV04
CTP Assist (under App Manager in Lightning) | Lightning App | Lightning App | Assign additional Edit access for Standard Object Permissions: | ASH | CTPDEV04
Live Agent Sessions
Live Chat Transcripts
Live Chat Visitors
Data management | Duplicate Rules and Matching Rules for Contact (Standard) |  | Need to verify the same in DEV05. | KD | CTPDEV04
Default Data Category Visibility | Default Data Category Visibility | CTP Assist | Default Data Category Visibility | KD | CTPDEV04
81 | Case to Data Category Mapping | CTP Assist | Case to Data Category Mapping | KD | CTPDEV04
82 | Data Category Assignments | CTP Assist | Data Category Assignments | KD | CTPDEV04

## FLS Post-Migration Sprint-2
Fields | FLS | Object
CTP_ActionDueDate__c |  | Case
Case.CTP_Date_of_accident__c |  | Case
Case.CTP_Next_Action_Status__c |  | Case
Case.CTP_LodgementDate__c |  | Case
CTP_InjuredPersonAccount__c |  | Case
CTP_InjuredPersonContact__c |  | Case
CTP_RepresentativeAccount__c |  | Case
CTP_RepresentativeContact__c |  | Case
CTP_RepresentativeRelationship__c |  | Case
CTP_OtherRelationshipDescription__c |  | Case
CTP_Date_of_accident__c |  | Case
CTP_LodgementDate__c |  | Case
CTP_DoNotContact__c |  | Case
CTP_DoNotContactReason__c |  | Case
CTP_ActionAndOutcome__c |  | Case
CTP_SeverityColor__c |  | Case
CTP_Severity__c |  | Case
CTP_SLAViolation__c |  | Case
CTP_NumberOfViolations__c |  | Case
Entitlement Name |  | Case
CTP_Discussion_Topic__c on article | Visible for All Profiles | Article
CTP_Talking_Points__c | Visible for All Profiles | Article
Feedback Type |  | Case
Feedback sub-type |  | Case
CTP_DateofBirth__c |  | Contact
CTP_PrimaryPhone__c |  | Contact
CTP_SecondaryPhone__c |  | Contact
CTP_ContactMethod__c |  | Contact
CTP_ContactTime__c |  | Contact
CTP_RepresentativeRelationship__c |  | Contact
CTP_RelationshipDescription__c | Hidden for All Profiles | Contact
CTP_Relationship__c | Hidden for All Profiles | Contact
CTP_Accessibility__c |  | Contact
CTP_Homeless__c |  | Contact
CTP Date Finalised on date | visible for CTP Assist and System Administrator
CTP_Answer | visible to all Profiles | Article
CTP_Discussion_Topic__c | visible to all Profiles | Article
CTP_Talking_Points1__c | visible to all Profiles | Article
CTP_Question__c | visible to all Profiles | Article
CTP_Steps__c | visible to all Profiles | Article
InterpreterRequired__c | visible to all Profiles | Contact
Language__c | visible to all Profiles | Contact
Standard Support Cases list view on case | arrange list view fiels in order Case Number, Claimants Name, Accident date, Case Priority, Case Status, Action Due Date, Case record type
talking points fields on article | make talking points visible and editable on system admin profile
talking points fields on article | make talking points visible and editable on ctp assist profile
discussion guide record type on article | select record type discussion guide on record type on admin profile
discussion guide record type on article | select record type discussion guide on record type on ctp assist profile
discussion topic field on article | make discussion topic visible and editable on system admin profile
discussion topic field on article | make discussion topic visible and editable on ctp assist profile
Question field on article | make Question visible and editable on system admin profile
Question field on article | make Question visible and editable on ctp assist profile
answer field on article | make answer visible and editable on system admin profile
answer field on article | make answer visible and editable on ctp assist profile
FAQ record type on article | select record type FAQ on record type on admin profile
FAQ record type on article | select record type FAQ on record type on ctp assist profile
How To record type on article | select record type How To record type on admin profile
How To record type on article | select record type How To record type on ctp assist profile
steps field on article | make steps field visible and editable on system admin profile
steps field on article | make steps field visible and editable on system admin profile
RecordTypeId field on HighLightForArticle compact layout | Please remove record type ID field while deploying and add it after deployment manually
Validation Status on article | add picklist values Reassigned, Pending, Approved, Rejected and Draft to Validation Status field on article manually
Date of Accident on case | visible to all profile on all app
Lodgement Date on case | visible to all profile on all app
CTP Date of Common Law Notification on case | visible to all profile on all app
Date Finalised on case | visible to all profile on all app
End date of service/benefit period on case | visible to all profile on all app
Accident Number on case | visible to all profile on all app
Fault Status on case | visible to all profile on all app
Risk Outcome on case | visible to all profile on all app
Fatality on case | visible to all profile on all app
Managing Insurer Code on case | visible to all profile on all app
Managing Insurer Claim Number on case | visible to all profile on all app
Minor Injury Decision on case | visible to all profile on all app
Outcome of WPI Assessment/Indication on case | visible to all profile on all app
Estimate of Injury Severity (EIS) on case | visible to all profile on all app
Statutory benefit liability Status on case | visible to all profile on all app
Common Law Liability Status on case | visible to all profile on all app
Claimant Capacity Status on case | visible to all profile on all app
Return to Work Status Code on case | visible to all profile on all app
picklist value 'Cancelled' on Status field on Task | value should be enabled for 'CTP Assist Task' record type only
ctp assist profile | enable read edit view all permisisons on article